INCEPTION REPORT

Submitted by

Technology Needs Assessment for Climate Change Mitigation and Adaptation in Lao PDR

NOVEMBER 2021

Table of Contents

1)	Introduction	2

1.1) Background and objectives	2

1.2) Progress in the inception phase	2

2)	Sectors and technologies	6

2.1) Long list of relevant sectors for adaptation	6

2.2) Long list of relevant sectors for mitigation	8

3)	Initial list of stakeholders	11

4)	Prioritization criteria	15

4.1) Sectors prioritization criteria for Adaptation	15

4.2) Sectors prioritization criteria for Mitigation	15

4.3) Technology options prioritization criteria	15

5)	Draft annotated table of contents	16

6)	Workplan	19

7)	Methodology note for sectors and technology prioritization	21

7.1) Justification for MCDA	21

7.2) Relative Importance Index	22

7.3) Prioritization approach	23

7.3.1) Methodology steps for MCDA	24

7.3.2) Application of AHP for prioritizing climate technologies	24

Annex 1: Kick-off meeting presentation	27

Annex 2: Initial questionnaire	31

# Introduction

# 1.1) Background and objectives

GGGI, in collaboration with the Green Climate Fund (GCF), Korea Development Bank (KDB), and the governments of Cambodia, Indonesia, Laos and the Philippines, seeks to accelerate the deployment of climate technologies at scale through the Climate Technopreneurship Project (CTP). The project will support deployment of climate technologies through new ventures and partnerships between global tech firms and selected local start-ups in the beneficiary countries. Such deployment of climate technologies will be achieved through a set of measures including incubation/acceleration services, financial support through an investment fund and technical assistance tailored to each country's needs. The objective of this assignment is to identify priority technology needs in Laos for climate change adaptation and mitigation in order to streamline the activities of CTP. The approach will start with a selection and prioritization of climate change relevant sectors in consultation with country stakeholders upon review of national climate change plans and strategies. Selection criteria will be applied using a multi criteria analysis alongside expert judgement for sectors most likely to reduce individual and community vulnerabilities to climate change as well as reduce GHG emissions in Laos. Similar to sectors prioritization process an assessment and prioritization of technologies in the priority sectors will be conducted, with the aim to inform on technology transfer and new technology opportunities that can assist Laos adopt a low carbon and climate resilient pathway.

# 1.2) Progress in the inception phase

During the inception stage, the methodology has been discussed with GGGI and the following outcomes came as part of the kick-off meeting:

- The technology needs assessment for Laos will have to integrate gender aspects given the relevance of gender to GGGI work.

- A tentative list of sectors will be provided during the inception phase, informed by existing climate plans and strategies for mitigation and adaptation in Laos.

- A tentative list of prioritization criteria for sectors and technologies will be provided at inception stage in order to cover choice of criteria in the consultative process as well.

- GGGI has an MoU with LNCCI which will be useful to address private sector associations and more broadly involve the private sector in the consultation process.

- A market assessment work is going in parallel with the technology needs assessment. The midterm report will be useful to inform on the specific financial instruments which the market assessment will focus on.

During the inception phase the following documents have been reviewed.

| Document reviewed | Summary of key take away relevant to TNA |
| --- | --- |
| Lao PDR TNA Report Adaptation | Two priority sectors chosen; water and agriculture. Eight technologies selected: four for water and four for agriculture. |
| Lao PDR TNA Report Mitigation | Two priority sectors chosen; forestry and agriculture. Eight technologies selected: four for forestry and four for agriculture. |
| National Socio-Economic Development Plan | Natural resources and the environment are effectively protected and utilised according to green-growth and sustainable principles; there is readiness to cope with natural disasters and the effects of climate change and for reconstruction following natural disasters. |
| National Strategy on Climate Change | This strategy sets goals and targets to 2030. (1) Mainstream, coordinate, and implement climate change mitigation and adaptation actions. (2) Enhance the resilience and adaptive capacity to reduce climate change vulnerability, risk and climate change induced disaster. (3) Reduce economic loss and damage from climate related disasters to less than 0.25% of GDP by 2025 and less than 0.2% of GDP by 2030 (4) Minimize the population to be affected by climate related disasters to less than 160,000 by 2025 and less than 120,000 by 2030. (5) Become a low emission country and reduce emissions to less than 0.6 t/cap/yr. by 2025 and <1.2 t/cap/yr. by 2030. (6) Fulfil mitigation and adaptation targets defined in updated NDCs and other relevant sectoral plans, strategies, and targets. |
| National Green Growth Strategy | Seven focused sectors were promoted to achieve the objectives and goals of the National Green Growth Strategy. (1) natural resources and environment (2) agriculture and forestry (3) industry and commerce (4) energy and mines (5) public works and transport (6) information, culture and tourism (7) science and technology |
| Lao PDR GCF Country Programme | Identified five priority areas; (1) Enhancing climate-resilient farming and communities (2) Supporting an increase and maintenance of national forest cover (3) Promoting emission reductions in the energy sector (4) Promoting low-carbon and climate-resilient urban development and transportation (5) Enhancing climate resilience in the public health sector |
| Lao PDR NDC | Mitigation: Sectors covered by the analysis include energy, industrial processes, agriculture, land-use change and forestry, and waste. Adaptation: Sectors covered by the analysis include agriculture, land-use change and forestry, water resources, transport and urban development, public health and energy. |
| TNA: Barrier Analysis & Enabling Framework (BAEF) for Adaptation | Focused on the BAEF for adaptation technologies and practices. Seven common barriers were identified (1) insufficient financial resources and support for development and deployment, (2) high investment cost (3) insufficient effective financing mechanisms, (4) insufficient technical knowledge and skills on the deployment of technologies for climate change adaptation and disaster resilience, (5) inadequate reporting and inaccurate information, (6) insufficient tools, best practices, technologies and reference projects, and (7) geographical difficulties including access by and unsustainable settlement of local people. |
| TNA: Barrier Analysis & Enabling Framework for Mitigation | Focused on the BAEF for mitigation technologies and practices Five common financial and economic barriers were identified (1) insufficient financial resources for promotion, development and management of the technologies (2) insufficient win-win financing and financial risk management mechanisms (3) low or not financial and economic feasibility for investment (4) marginal profit while investment cost is high (5) inadequate financial and economic incentives including subsidies Six common non-financial and economic barriers were identified (1) insufficient skills for promotion, development and management of the technologies (2) limited financial, economic and technical feasibility studies and information (3) technical difficulty and utility limitation of the technologies (4) inadequate reference projects such as successful interventions and best practices (5) insufficient policy framework (6) variable markets |
| TAP for Climate Change Adaptation | Focused on the TAP for the following eight adaptation technologies and practices Water Resources (1) Early warning system (2) Disaster impact reduction fund (3) River basin management (4) Climate-resilient water supply system Agriculture (5) Livestock disease prevention and control (6) Agricultural development subsidy mechanism (7) Climate-resilient rural infrastructure (8) Crop diversification |
| TAP for Climate Change Mitigation | Focused on the TAP for the following eight mitigation technologies and practices Forestry (1) Effective conservation forest management/protected area management (2) Sustainable village forest management (3) Optimal or sustainable plantation forests (4) Optimal agroforestry Agriculture (1) Feed improvement (2) Organic farming (3) Biogas (4) Biomass |
| National Adaptation Programme of Action to Climate Change (NAPA) | Identified adaptation objectives and priorities for the agriculture, forestry, water resource, and health sectors during 2010–2020. As of 2021 many of these priorities remain critical, such as (i) early warning systems, (ii) programs to boost the resilience of crop varieties and animal species to climate change, and (iii) ensuring sustainable use of water resources. |

Initial prioritization criteria have been identified for adaptation and mitigation on sectors and technologies. Chapter 4 proposes the initial criteria.

An initial set of questions has also been compiled with technology options on proposed sectors. Annex 2 below outlines the initial set of questions for mitigation and adaptation. These questions will be further discussed and processed within an online survey that will be sent to the long list of stakeholders for sectors and technology prioritization.

The tool for Multi-Criteria Decision Analysis (MCDA) has also been identified. The prioritization approach will use Relative Importance Index (RII), steps and computation approach are outlined in Chapter 8 below.

# Sectors and technologies

Document review has led to a list of sectors and sub-sectors for mitigation and adaptation, the long list. The prioritization methodology described in this report will lead to determination of climate change mitigation and adaptation sectors and sub-sectors needs. Priority technologies will be technologies related to priority sub-sectors.

# 2.1) Long list of relevant sectors for adaptation

| Sector | Laos Climate Change Adaptation Objectives |
| --- | --- |
| Agriculture | - Promote climate resilience in farming systems and agriculture Infrastructure - Promote appropriate technologies for climate change adaptation, including nature-based and circular economy solutions |
| Land Use Change and Forestry (LUCF) | - Promote climate resilience in forestry production and forest ecosystems, including in buffer zones of protected areas and other forested areas - Promote technical capacity in the forestry sector for managing forest for climate change adaptation - Promote integrated land use planning, natural resources and environment management |
| Water Resources | - Strengthen water resource information systems for climate change adaptation - Manage surface water, groundwater and wetland for climate change resilience - Increase water resource infrastructure resilience to climate change, including through nature-based solutions - Strengthen early warning systems in a timely manner |
| Transport and Urban Development | - Increase the resilience of urban development and infrastructure to climate change, including through the use of green infrastructure and nature-based solutions - Promote ecosystem-based adaptation solutions |
| Public Health | - Increase the resilience of public health infrastructure and water supply system to climate change - Improve public health services for climate change adaptation and coping with climate change induced impacts. |
| Climate Resilient Energy Infrastructure | - Build resilience to climate change in hydropower sector through improved dam safety regulations and guidelines - Strengthen technical capacity to use new and innovative technologies to enhance climate resilience and sound management in energy sector - Promote multipurpose use of reservoirs to enhance resilience of surrounding communities and maximize benefits for other sectors |
| Early Warning System | - Develop and enhance the capacity for management of data and reporting system on climate change, and the end-to-end early warning systems. - Strengthen capacity on climate change monitoring, assessment, reporting, communication, and response planning. - Assessment of vulnerability including mapping and profiling climate hazards. |
| Climate Resilient Buildings | - Strengthening resilience by conducting studies and assessments of climate change impacts, vulnerability and risks on buildings. - Enhance research, development and transfer of technologies to strengthen resilience and adaptive capacity of buildings. - Develop and implement regulations, standards, strategies and plans on adaptation and investment in climate resilient buildings. |

# 2.2) Long list of relevant sectors for mitigation

| Sector | Laos Climate Change Mitigation Objectives |
| --- | --- |
| Agriculture | - Enhance low-emission and environmentally friendly practices such as smart and precise farming, feeds-feeding and livestock manure management. - 50,000 hectares adjusted water management practices in lowland rice cultivation. - Increase animal feeds of 1.4 million tons by 2025, including 1% of feed and concentrates that reduce emissions. |
| Land Use Change and Forestry (LUCF) | - Reduced emissions from deforestation and forest degradation, foster conservation, sustainable management of forests, buffer zones of national parks and other preserves, and enhancement of forest carbon stocks. - Reduction of LUCF emissions by 1,100ktCO2e per year on average between 2020 and 2030. - Promote protection and development of the forests carbon and nitrogen sequestration and storage. - Enhance forest restoration and rehabilitation. - Strengthen sustainable forest and non-timber forest product management. |
| Energy Production and Supply | - Promote introduction of 50,000 energy efficient cook stoves. - 13GW total hydropower capacity (domestic and export use) in the country. - Solar and Wind: 1 GW total installed capacity in the country. - Biomass: 300 MW total installed capacity in the country. - 10% reduction of final energy consumption compared to business-as-usual scenario. - Promote energy saving and efficiency building design and appliances. - Enhance marketing, promotion, awareness raising and implementation of policies on energy efficiency and savings. |
| Transport and Urban Development | - Improve and develop urban and road network, transport, and logistics systems to reduce traffic congestion. - Promote low emission urban planning, infrastructure, transportation, non- motorized transportation operations. - Promote development and use of electric vehicles. - 30% electric vehicles penetration for 2-wheelers and passengers' cars in national vehicles mix. - Biofuels to meet 10% of transport fuels. |
| Industry | - Promote deployment of capture and storage technologies in large industries. - Enhance research, piloting and promotion of development of environmental standards in large industries. |
| Waste | - Enhance low-emission waste management, including promoting the 3Rs of waste management (reduce, reuse, and recycle) and waste-to-energy. - Improve wastewater treatment and use of gas as energy. - Implementation of 500 tons/day sustainable municipal solid waste management project. |

# Initial list of stakeholders

A list of 64 stakeholders has been identified alongside the 4 targeted groups of stakeholders to consult: Government, Private sector, Academia/Researcher, and Civil Society Organisations. These stakeholders will be sent the online questionnaire. Data collected through the online questionnaire and expert judgement will be used to identify priority sectors. In case needed, stakeholders from the short list of sectors will be contacted for additional clarification through online interviews. The following is the initial list of stakeholders:

| # | Organisation/Institution | Type of Organisation/Institution | Sector |
| --- | --- | --- | --- |
| 1 | Department of Climate Change (DCC)- Ministry of National Resources & Environment (MoNRE) | Government | Multiple |
| 2 | Lao National Chamber of Commerce and Industry (LNCCI) | Private | Multiple |
| 3 | Institute of Renewable Energy Promotion, MEM | Research Institute | Energy Generation & Access |
| 4 | Department of Environment Promotion-MoNRE | Government | Multiple |
| 5 | Department of Water Resources-MoNRE | Government | Water |
| 6 | Department of Land Management-MoNRE | Government | AFOLU |
| 7 | Department of Meteorology & Hydrology-MoNRE | Government | Water |
| 8 | Natural Resources & Environment Research Institute | Research Institute | Multiple |
| 9 | Department of Agriculture, Ministry of Agriculture and Forestry (MAF) | Government | Agriculture |
| 10 | Department of Livestock & Fishery, MAF | Government | Agriculture |
| 11 | Department of Irrigation, MAF | Government | Water |
| 12 | Department of Agriculture and Forestry Extension Services, MAF | Government | AFOLU |
| 13 | National Agriculture & Forestry Research Institute (NAFRI), MAF | Research Institute | AFOLU |
| 14 | Department of Forestry, MAF | Government | Forestry |
| 15 | Faculty of Forestry, National University of Laos (NUoL) | Academia | Forestry |
| 16 | Department of Energy Management, Ministry of Energy & Mines (MEM) | Government | Industries & Energy Efficiency |
| 17 | Center for Malaria Control, Ministry of Public Health (MPH) | Government | Health & Well-Being |
| 18 | Center for Water Sanitation & Hygiene, MPH | Government | Health & Well-Being |
| 19 | Department of Transport, Ministry of Public Works & Transport (MPWT) | Government | Low-Emission Transport |
| 20 | Department of Urban Planning & Housing, MPWT | Government | Urban Planning |
| 21 | Public Work & Transport Research Institute, MPWT | Research Institute | Low-Emission Transport |
| 22 | Faculty of Environment Science, UNoL | Academia | Multiple |
| 23 | Department of Technology & Innovation, Ministry of Science & Technology (MST) | Government | Multiple |
| 24 | Renewable Energy Research & Development Center, MST | Research Institute | Energy Generation & Access |
| 25 | National Economic Research Institute (NERI), Ministry of Planning & Investment (MPI) | Research Institute | Most Vulnerable People & Communities |
| 26 | Department of International Personnel, Department of Foreign Affairs (DoFA) | Government | Multiple |
| 27 | Department of International Finance, DoFA | Government | Multiple |
| 28 | Department of Industry Process, Ministry of Industry and Commerce (MIC) | Government | Industries & Energy Efficiency |
| 29 | International Rice Research Institute (IRRI) | International Organization | Agriculture |
| 30 | Mekong River Commission (MRC) | International Organization | Multiple |
| 31 | International Union for Conservation of Nature (IUCN) | International Organization | Ecosystems & Ecosystem Services |
| 32 | UNDP | International Organization | Multiple |
| 33 | World Bank | International Organization | Multiple |
| 34 | National Statistic Center (NSC) | Government | Multiple |
| 35 | Lao Development Bank | Private | Multiple |
| 36 | Department of Planning & Cooperation, MAF | Government | AFOLU |
| 37 | Department of Planning & Cooperation, MEM | Government | Efficient Buildings |
| 38 | Department of Pollution Control, MoNRE | Government | Health & Well-Being |
| 39 | National Disaster Management Office, Ministry of Labour & Social Welfare | Government | Early Warning Systems |
| 40 | Agriculture Promotion Bank | Private | Agriculture |
| 41 | Banque Franco Lao | Private | Multiple |
| 42 | Banque pour le Commerce Exterieur Lao Public | Private | Multiple |
| 43 | Joint Development Bank | Private | Multiple |
| 44 | New Chip Xeng Co. | Private | Low-Emission Transport |
| 45 | Lao Biodiversity Association | Civil Society Organization | Ecosystems & Ecosystem Services |
| 46 | Lao Women’s Union | Civil Society Organization | Multiple |
| 47 | Lao Youth Union | Civil Society Organization | Multiple |
| 48 | GiZ | International Organization | Multiple |
| 49 | Lao National Mekong Committee | International Organization | Multiple |
| 50 | Earth Systems Mekong | Private | Multiple |
| 51 | Japan International Cooperation Agency | International Organization | Multiple |
| 52 | Korea International Cooperation Agency | International Organization | Multiple |
| 53 | REDD Office, Department of Forestry, MAF | Government | Forestry |
| 54 | Environment Protection Fund | Government | Ecosystems & Ecosystem Services |
| 55 | Lao Business Women Association, LNCCI | Private | Multiple |
| 56 | Lao Young Entrepreneur Association, LNCCI | Private | Multiple |
| 57 | Lao Agro-Processing Association, LNCCI | Private | Agriculture |
| 58 | Lao Petroleum & Gas Association, LNCCI | Private | Low-Emission Transport |
| 59 | Lao Cement Producers Group, LNCCI | Private | Industries & Energy Efficiency |
| 60 | Burapha Agroforestry Co.Ltd | Private | AFOLU |
| 61 | Provincial Agriculture & Forestry Office, Xieng Khouang | Government | AFOLU |
| 62 | Forage and Livestock Farm, Xieng Khouang | Private | Agriculture |
| 63 | AustCham Laos | Private | Multiple |
| 64 | European Chamber of Commerce and Industry in Lao PDR | Private | Multiple |

# Prioritization criteria

# 4.1) Sectors prioritization criteria for Adaptation

For the Multi Criteria Analysis, we propose the following criteria for prioritization of sectors on Adaptation

- contribution to country national climate targets

- Potential to improve resilience of most vulnerable communities

- Potential to improve country economic situation

- Contribution to SDGs

- Potential to improve social conditions with gender equality benefits

- Potential to generate environmental benefits

# 4.2) Sectors prioritization criteria for Mitigation

For the Multi Criteria Analysis, we propose the following criteria for prioritization of sectors on Mitigation

- Potential to significantly reduce country´s GHG emissions

- Countribution to National Mitigation Targets (with consideration to staying on track with 1.5 °C target)

- Potential to improve GDP/country economic situation

- Contribution to SDGs

- Potential to improve social conditions with gender equality benefits

- Potential to generate environmental benefits

# 4.3) Technology options prioritization criteria

We will consider only technologies within most important sub-sectors. We propose using the following criteria for prioritization of technology options.

- Relative cost/efficiency: cost will be based on benchmarks and publicly available information for cost of given technology. The magnitude will consider climate change targets of the county. When cost is not available, this criterion will be set to neutral.

- Impact Potential: The potential impact which a given technology can generate for climate change mitigation or adaptation. Impact potential will be quantified in GHG emissions reduction potential for mitigation and number of potential beneficiaries for adaptation.

- Relevance: How relevant the specific technology is compared to country´s climate objectives.

- Gender equality benefits: How can the technology contribute to promote gender equality in the country.

- Sustainability/lifetime: The potential which the specific technology has to achieve long term social, economic and environmental benefits.

# Draft annotated table of contents

Executive Summary

- The executive summary will present the key findings of the assessment.

- It will include an overview of development priorities, possible climate change impacts for Lao PDR, justification of the chosen priority (sub) sectors, description of the present situation in the prioritized sectors, description of the evaluation criteria, summary of the prioritized technologies and a summary of a national strategy/action plan for the acceleration of the prioritized technologies.

- The executive summary will provide a sense of the required “national actions” to move forward.

Chapter 1: TNA process overview

1.1 TNA objective

- Brief description of why countries’ conduct the assessment, and the main outcomes of the process.

1.2 Linkages with Lao PDR national policies

- This section will outline how the TNA is linked with national policy actions in the field of sustainable development and climate change policy making.

- A table of relevant national policies/plans will be included in this section.

1.3 Stakeholder identification process

- An explanation of the process by which stakeholders were identified, recruited and engaged.

- A definitive list of stakeholders by type and sector.

1.4 Distinctions between mitigation and adaptation processes

- Identification of distinctions between mitigation and adaptation processes.

1.5 TNA methodology

- This section will describe the major steps followed in conducting the TNA process. It will show that the process was embedded in a multi-stage process.

Chapter 2: Identification of development priorities for Lao PDR

2.1 Current development priorities

- A background regarding the sector-specific plans and priorities currently in place in the country and which new technologies for mitigation and adaptation would be introduced.

2.2 Long-term development priorities

- A description of the long term vision for the country from which a list of development priorities are presented, which are grouped as economic, environmental and social priorities.

2.3 Implications of climate change for Lao PDR

- A description on the discussion on the short and long term implications of climate change for Lao PDR.

- A list of needs for technology for combating climate change in Lao PDR will be included in this section.

Chapter 3: Adaptation

3.1 Identification of adaptation key sectors/sub-sectors for low emission and low vulnerability development

3.1.1 Sector/sub-sector prioritization process

- This section will discuss the prioritization process adopted for prioritizing adaptation(sub)sectors, including the criteria used and the output of the assessment made for the identification of priority adaptation (sub)sectors.

3.1.2 Key sectors/sub-sectors

- A definitive list of key sectors/sub-sectors derived from the results of the prioritization process.

- The list will include the top three priority sectors for adaptation.

3.1.3 Key sectors/sub-sectors technology use and plans

- A discussion on technology-related aspects of the selected adaptation sectors/sub-sectors.

- This section will include the results of a market assessment of green and climate technologies in Laos, covering all types of engagement with legally registered companies and the VC industry.

3.2 Prioritization of adaptation technologies for low emission and low vulnerability development

3.2.1 MCDA/AHP process

- A definition of the criteria used, the value tree, the scores and justification for the scores on the criteria, the weightings derived and their justification.

3.2.2 Initial results and sensitivity analysis of the priority technologies for adaptation

- Presentation of initial results and the subsequent sensitivity analysis.

- An exploration of the uncertainties and differences in perspectives.

- Identification of robust priority technologies for adaptation.

3.2.3 Summary of the priority technologies for adaptation

- Tabular summary of the priority technologies for adaptation.

- Adaptation potential of prioritized technologies in each sector.

Chapter 4: Mitigation

4.1 Identification of mitigation key sectors/sub-sectors for low emission and low vulnerability development

4.1.1 Sector/sub-sector prioritization process

- This section will discuss the prioritization process adopted for prioritizing mitigation (sub)sectors, including the criteria used and the output of the assessment made for the identification of priority mitigation (sub)sectors.

4.1.2 Key sectors/sub-sectors

- A definitive list of key sectors/sub-sectors derived from the results of the prioritization process.

- The list will include the top three priority sectors for mitigation.

4.1.3 Key sectors/sub-sectors technology use and plans

- A discussion on technology-related aspects of the selected mitigation sectors/sub-sectors.

- This section will include the results of a market assessment of green and climate technologies in Laos, covering all types of engagement with legally registered companies and the VC industry.

4.2 Prioritization of mitigation technologies for low emission and low vulnerability development

4.2.1 MCDA/RII process

- A definition of the criteria used, the value tree, the scores and justification for the scores on the criteria, the weightings derived and their justification.

4.2.2 Initial results and sensitivity analysis of the priority technologies for mitigation

- Presentation of initial results and the subsequent sensitivity analysis.

- An exploration of the uncertainties and differences in perspectives.

- Identification of robust priority technologies for mitigation.

4.2.3 Summary of the priority technologies for mitigation

- Tabular summary of the priority technologies for mitigation.

- Total GHG reduction potential technologies in each sector.

Chapter 5: Conclusions and recommendations

- Highlighting the main conclusions and recommendations of the TNA.

Annexes

- Annex 1: List of key stakeholders involved in the TNA process

- Annex 2: Sectors/sub-sectors covered in the inventory and mitigation

- Annex 3: Sensitivity analysis of the criteria and score of technologies

- Annex 4: Technology factsheets for selected technologies

# Workplan

| Week | Activity | Tasks to be performed | Who | Deliverables |
| --- | --- | --- | --- | --- |
| 1 | Inception Meeting Data collection | Discuss the initial scope of the study Collection of relevant national documents for desk review | GGGI Lao PDR & Climate Platform (CP) GGGI Lao PDR & CP | Initial scope of study Relevant document submission |
| 2 | Tentative list of sectors Identify stakeholders Work plan Inception Report | Analysis of existing TNA Data collection on GHG emissions and/or adaptation capacity/vulnerability reduction potential Analysis of existing TNA and other relevant country documents, recommendations from GGGI Compilation of work plan and timetable Drafting of Inception Report | CP CP CP & GGGI Lao PDR CP CP | Tentative list of priority (sub) sectors for mitigation and adaptation Definitive list of stakeholders Initial work plan and timetable Submission of Inception Report |
| 3 | Identification of development priorities for Lao PDR Feedback (if needed) Finalize (sub)sectors Market Assessment | Analysis of current/ long-term development priorities & implications of climate change for the country Discussion session Consultations on the finalization of (sub)sectors Market assessment of green and climate technologies in Lao PDR | CP GGGI Lao PDR & CP CP & GGGI Lao PDR CP | Background of current plans & description of long-term vision for Lao PDR Suggestions to be incorporated in mid-term report Final list of (sub)sectors Completed market assessment |
| 4 | Map of (sub)sectors technologies Questionnaires | Mapping (sub) sectors technologies Finalizing and sending questionnaires to long-list of stakeholders | CP CP & stakeholders | Map of (sub) sectors technologies Completed questionnaires submitted by CP |
| 5 | Data collection Interviews (on demand) Prioritization | Tracking progress of questionnaires Conduct interviews with key stakeholders MCDA/AHP | CP CP & stakeholders CP | Progress of questionnaires Report of stakeholder interviews Tabular summary of priority (sub) sectors & technologies for mitigation/ adaptation |
| 6 | Christmas (CP consultants will be on leave) |  |  |  |
| 7 | Sensitivity analysis Mid-term report | Sensitivity analysis to determine the robustness of the priority technologies Drafting of mid-term report | CP CP | Completed sensitivity analysis Submission of mid-term report |
| 8 | Feedback on mid-term report | Discussion session | CP & GGGI Lao PDR | Suggestions to be incorporated into draft final report |
| 9 | Draft final report | Drafting of final report | CP | Submission of draft final report |
| 10 | Draft final report | Drafting of final report | CP | Submission of draft final report |
| 11 | Feedback on draft final report | Discussion session | GGGI Lao PDR & CP | Suggestions to be incorporated into final report |
| 12 | Final Report | Drafting of final report | CP | Submission of final report |

# Methodology note for sectors and technology prioritization

# 7.1) Justification for MCDA

Identifying priority sectors and sub-sectors for climate intervention, and ranking the most suitable technology options that can support a country's climate strategic action and accelerate technology transfer often result in conflicting scenarios for technology requirements. Multi-Criteria Decision Analysis (MCDA) is therefore used to cluster priorities and rank sectors and technologies based on the importance of their contribution for climate change adaptation and mitigation. MCDA tool will be employed to deal with decision problems among conflicting scenarios, as well as minimize uncertainties in the decision process. This tool would be used to identify and rank climate technologies by importance for climate adaptation and mitigation from a set of criteria defined through a participatory and inclusive process.

# 7.2) Relative Importance Index

Relative Importance Index (RII) would be used to determine the relative importance of quality factors (evaluation criteria). The following steps would be employed:

- Identify the factors - Proposed factors are in section 4 of this report

- Collect data from stakeholders on the relative importance of criteria

- Determine the RII based on responses

For example:

Question:  The following evaluation criteria are the most important for GHG mitigation in the agriculture sector

|  | Strongly agree (5) | Agree (4) | Neutral (3) | Disagree (2) | Strongly disagree (1) |
| --- | --- | --- | --- | --- | --- |
| Contribution to country national climate targets | n | n | n | n | n |
| Potential to improve resilience of most vulnerable | n | n | n | n | n |
| Potential to improve country economic situation | n | n | n | n | n |
| Contribution to SDGs | n | n | n | n |  |

# 7.3) Prioritization approach

The list of all potential sectors and sub-sectors that can contribute to achieving climate change mitigation and adaptation in Laos is derived from the review of all climate strategic documents presented in section 1.2.  We will use a Two-Dimensional Priority Scheduling (TDPS) to determine which technologies are a priority in supporting Laos achieve its climate objectives on both mitigation and adaptation. First the MCDA will help rank sectors and technologies by order of importance. The importance to climate change mitigation and adaptation will enable come with the top sectors and sub-sectors however this is not sufficient to prioritize technology transfer interventions given scarce financial resources for technology transfer and ongoing market dynamics. The TDPS will introduce the concept of technology availability in the market, leading to 4 clusters of priority for technology investments as described in the diagram below.

P1 Technology importance to climate adaptation/mitigation Technology availibility P2 P3 P4

Where,

- P1 are technologies with high importance in terms of contributing to climate change mitigation and adaptation and currently not available in Laos,

- P2 are technologies with high importance in terms of contributing to climate change mitigation and adaptation but currently already in use in Laos,

- P3 are technologies with limited or low potential contribution to climate mitigation or adaptation and not in use in Laos

- P4 are technologies with limited or low contribution to climate change mitigation or adaptation and already available in Laos.

The TNA will recommend investment in P1 technologies with budgets and financial allocations dedicated to technology transfer, and P2 investments for budgets and financial allocations dedicated to climate change adaptation and mitigation with local content.

# 7.3.1) Methodology steps for MCDA

In this project, the Analytic Hierarchy Process (AHP) is the MCDA tool that would be used because it is a powerful yet simple method for making decisions, and it is the most widely used (MCDA) tool for project selection and prioritization. The following steps would be employed:

Step 1: Identify lists of sectors, subsectors and climate technologies

Step 2: Establish evaluation criteria for sectors, sub-sectors and climate technologies

Step 3: Evaluate sectors, sub-sectors and technologies in terms of selected criteria

Step 4: Apply a normative multi-criteria analysis method

Step:5: Rank sectors, sub-sectors and climate technologies

# 7.3.2) Application of AHP for prioritizing climate technologies

a.      Structure the decision problem into a hierarchical model starting with the main goal at the top, followed by criteria, and alternatives at the bottom.

For example:

b.       Construct a pair-wise comparison and obtain the judgmental matrix by assigning a numerical value.

For example:

|  | Technology 1 | Technology 2 | Technology 3 | Technology 4 |
| --- | --- | --- | --- | --- |
| Technology 1 | 1 | 1 | 6 | 1/2 |
| Technology 2 | 1 | 1 | 6 | 1/2 |
| Technology 3 | 1/6 | 1/6 | 1 | 1/7 |
| Technology 4 | 2 | 2 | 7 | 1 |

Comparison based on Saaty scale:

| Intensity of importance | Definition |
| --- | --- |
| 1 | Equal importance |
| 2 | Equal to moderate importance |
| 3 | Moderate importance |
| 4 | Moderate to strong importance |
| 5 | Strong importance |
| 6 | Strong to very strong importance |
| 7 | Very strong importance |
| 8 | Very to extremely strong |
| 9 | Extreme importance |

c.       Compute weight of compared elements by Equation below:

where: wi is the corresponding normalized Eigen vector (local priority) and n is the number of compared elements

d.       Determine the consistency index (CI) and consistency ratio (CR) by applying Eqs. (2), (3) respectively.

Where, λmax is the largest real Eigen value of comparison matrix and n is the matrix size.

where,

RI is the random consistency index, determined from the RI scale. If the CR is less than 0.1, then the judgment matrix is said to be consistent, if not, the process has to be performed again to give a consistent lev

# Annex 1: Kick-off meeting presentation

# Annex 2: Initial questionnaire

Technology Needs Assessment for Climate Change Adaptation and Mitigation Technology in Lao PDR

The Global Green Growth Institute (GGGI) in collaboration with the Green Climate Fund (GCF), Korea Development Bank (KDB), and the government of Laos seek to accelerate the deployment of climate technologies at scale through the Climate Technopreneurship Project. This survey is being undertaken by the Climate Platform as the preparatory phase of the project to identify priority sectors and technologies for Laos to meet its adaptation and mitigation needs.

- Personal data

- Location…..

- Gender………

- Respondents group

- Government worker

- Private sector worker

- Academia/Research

- Civil society organization

- Which organization are you a representative of?

- Please see list of stakeholders

- Please choose one impact area for which you would want to answer

- Climate change adaptation

- Climate change mitigation

- Relative importance of evaluation criteria for adaptation

- The following evaluation criteria are the most important for selection of priority sectors for climate intervention

- Contribution to country national climate targets

- Potential to improve resilience of most vulnerable communities

- Potential to improve country economic situation

- Contribution to SDGs

- Potential to improve social conditions with gender equality benefits

- Potential to generate environmental benefits

- The following evaluation criteria are the most important for climate change technology

- Relative cost/efficiency

- Impact Potential

- Relevance

iv. Gender equality benefits

v. Sustainability/lifetime

- Priority sectors for adaptation

- What is the top priority sector for climate change adaptation in Laos?

- Agriculture

- Water Resources

- Transport and Urban Development

- Energy

- Industry

- Public health

- What is the second priority sector for climate change adaptation in Laos?

- Agriculture

- Water Resources

- Transport and Urban Development

- Energy

- Industry

- Public health

- What is the third priority sector for climate change adaptation in Laos?

- Agriculture

- Water Resources

- Transport and Urban Development

- Energy

- Industry

- Public health

C.1. Agriculture sector

- What is the top priority sub-sector for climate change adaptation in Laos' agriculture sector?

- Crop management

- Livestock

- Fisheries

- Forestry

- What is the second priority sub-sector for climate change adaptation in Laos' agriculture sector?

- Crop management

- Livestock

- Fisheries

- Forestry

- What is the third priority sub-sector for climate change adaptation in Laos' agriculture sector?

- Crop management

- Livestock

- Fisheries

- Forestry

C.1.1. Crop management

14. What are the top three priority technologies for crop management?

- Crop diversification

- Pest management or control

- Seeds bank and storage

- Integrated cropping system

- Organic farming

- Adjusting cropping seasons

- Integrated nutrient management

- Agro-forestry

- Irrigation schemes

C.1.2 Livestock

15. What are the top three priority technologies for Livestock?

- Livestock disease control

- Livestock health promotion

- Feeds and feeding improvement

- Selective breeding via controlled mating

- Early warning systems and insurance

- Biotechnology techniques (genetic improvement)

C.1.3 Fishery

16. What are the top three priority technologies for fishery production?

- Closed containment

- Aquaculture

- Smart fishing and weighing

- Advanced storage system

C.1.4 Forestry

17. What are the top three priority technologies for the forestry sub-sector?

i. Precision forestry (Unmanned Aerial Systems)

ii. Sustainable forestry management

- Flood and drought management

- Research tools

C.2. Water resources sector

18. What is the top priority sub-sector for climate change adaptation in Laos' water resources sector?

i. Water sources and supply management

ii. Water quality management

iii. Flood and drought management

iv.Water efficiency

19. What is the second priority sub-sector for climate change adaptation in Laos' water resources sector?

i. Water sources and supply management

ii. Water quality management

iii. Flood and drought management

iv. Water efficiency

20. What is the third priority sub-sector for climate change adaptation in Laos' water resources sector?

i. Water sources and supply management

ii. Water quality management

iii. Flood and drought management

iv. Water efficiency

C.2.1. Water sources and supply management

21. What are the top four priority technologies for water sources and supply management?

i. Watershed management (IWRM)

ii. Ground water pump

- Multi-purpose hydropower dam

- Irrigation

- Borehole/Tube wells

- Rain water harvesting

- Water safety plan

C.2.2. Water quality management

22. What are the top four priority technologies for water quality management?

i. Water quality monitoring

ii. Effective law enforcement

iii. Water treatment plants

iv.Water recycles

- Water drainage system

- Household drinking water treatment and safe storage

- River bank protection

C.2.3. Flood and drought management

23. What are the top four priority technologies for flood and drought management?

i. Early warning system

ii. Flood and drought hazard mapping

iii. Flood and drought monitoring

iv.Improve weather forecast system

v.Regulation of water discharge (from dam)

vi. Preservation of wetland

C.2.4. Water efficiency

24. What is the top priority technology for water efficiency?

i. Water resources awareness and education

ii. Smart sensors for distribution

C.3. Transport and urban development sector

25. What is the top priority sub-sector for climate change adaptation in Laos' Transport and urban development sector?

i. Airlines

ii. Marine

iii.Road

iv.Rail,

v.Transportation infrastructure

26. What is the second priority sub-sector for climate change adaptation in Laos' transport and urban development sector?

i. Airlines

ii. Marine

iii.Road

iv.Rail,

v.Transportation infrastructure

27. What is the third priority sub-sector for climate change adaptation in Laos' Transport and urban development sector?

i. Airlines

ii. Marine

iii.Road

iv.Rail

v.Transportation infrastructure

C.3.1. Airlines

28. What are the top three priority technologies for Airlines?

i. Energy management strategy

ii. Robotics

iii. Digital Twins

iv. AI & Machine Learning

C.3.2. Marine

29. What are the top three priority technologies for Marine sub-sector?

i. Energy management strategy

ii. Robotics

iii. Digital Twins

iv. AI & Machine Learning

C.3.3. Road

30. What are the top three priority technologies for Road sub-sector?

i. Energy management strategy

ii. Robotics

iii. Digital Twins

iv. AI & Machine Learning

C.3.4. Rail

31. What are the top three priority technologies for Rail sub-sector?

i. Energy management strategy

ii. Robotics

iii. Digital Twins

iv. AI & Machine Learning

C.3.5. Transport and infrastructure

32. What are the top three priority technologies for transport and infrastructure?

i. Energy management strategy

ii. Robotics

iii. Digital Twins

iv. AI & Machine Learning

C.4. Energy sector

33. What is the top priority sub-sector for climate change adaptation in Laos' energy sector?

- Solar energy generation

- Hydro energy generation

- Wind energy generation

- Gas-based generation

- Coal-based generation

- Nuclear power generation

34. What is the second priority sub-sector for climate change adaptation in Laos' energy sector?

- Solar energy generation

- Hydro energy generation

- Wind energy generation

- Gas-based generation

- Coal-based generation

- Nuclear power generation

35. What is the third priority sub-sector for climate change adaptation in Laos' energy sector?

- Solar energy generation

- Hydro energy generation

- Wind energy generation

- Gas-based generation

- Coal-based generation

- Nuclear power generation

C.4.1. Solar energy generation

36. What is the top priority technology for solar energy generation?

i. Solar thermal

ii. Concentrating solar power

iii. Small photovoltaic

iv. Large photovoltaic

C.4.2. Hydro energy generation

37. What is the top priority technology for hydro energy generation?

i. Hydro turbine

ii. Hydrokinetic turbines

C.4.3. Wind energy generation

38. What is the top priority technology for wind energy generation?

i. Onshore Wind

ii. Offshore Wind

C.4.4. Gas-based generation

39. What are the top two priority technologies for wind energy generation?

i. Conventional combustion turbine

ii. Advanced combustion turbine

iii.Natural gas combined cycle

iv.Advanced natural gas combined cycle

C.4.5. Gas-based generation

40. What are the top two priority technologies for wind energy generation?

i. Single Unit APC

ii. Double Unit APC

iii.Single Unit APC with CCS

iv.Double Unit APC with CCS

C.5. Industry sector

41. What is the top priority sub-sector for climate change adaptation in Laos' industry sector?

- Mineral industry

- Chemical industry

- Metal Production

- Food products

42. What is the second priority sub-sector for climate change adaptation in Laos' industry sector?

i.	Mineral industry

ii. Chemical industry

iii. Metal Production

iv. Food products

43. What is the third priority sub-sector for climate change adaptation in Laos' energy sector?

i. Mineral industry

ii. Chemical industry

iii. Metal Production

iv. Nuclear power generation

v. Food products

C.5.1. Mineral industry

44. What is the top priority technology for the mineral industry?

i. Cement production

ii. Glass production

iii. asphalt roofing production

C.5.2. Chemical industry

45. What is the top priority technology for the chemical industry?

i. Ammonia and urea fertilizer

ii. Nacl

C.5.3. Metal Production

46. What is the top priority technology for metal production?

i. Steel

ii. Ferroalloy production

C.5.4. Food products

47. What is the top priority technology for food production?

i. Soft drinks/beverages

ii. Alcoholic drinks

iii. Sugar

iv. Flour products (biscuits, pasta etc)

- Relative importance of evaluation criteria for mitigation

- The following evaluation criteria are the most important for selection of priority sectors for climate intervention

- Potential to significantly reduce country´s GHG emissions

- Countribution to National Mitigation Targets (with consideration to staying on track with 1.5 °C target)

- Potential to improve GDP/country economic situation

- Contribution to SDGs

- Potential to improve social conditions with gender equality benefits

- Potential to generate environmental benefits

- The following evaluation criteria are the most important for climate change technology

- Relative cost/efficiency

- Impact potential

- Relevance

- Gender equality benefits

- Sustainability/lifetime

- Priority sectors for mitigation

- What is the top priority sector for climate change mitigation in Laos?

- Agriculture

- Water Resources

- Transport and Urban Development

- Energy

- Industry

- Public health

- What is the second priority sector for climate change mitigation in Laos?

i.	Agriculture

ii.	Water Resources

iii.	Transport and Urban Development

iv.	Energy

v.	Industry

vi.	Public health

- What is the third priority sector for climate change mitigation in Laos?

- Agriculture

- Water Resources

- Transport and Urban Development

- Energy

- Industry

- Public health

E.1. Agriculture sector

- What is the top priority sub-sector for climate change mitigation in Laos' agriculture sector?

- Crop management

- Livestock

- Fisheries

- Forestry

- What is the second priority sub-sector for climate change mitigation in Laos' agriculture sector?

- Crop management

- Livestock

- Fisheries

- Forestry

- What is the third priority sub-sector for climate change mitigation in Laos' agriculture sector?

- Crop management

- Livestock

- Fisheries

- Forestry

E.1.1. Crop management

56. What are the top three priority technologies for crop management?

- Crop diversification

- Pest management or control

- Seeds bank and storage

- Integrated cropping system

- Organic farming

- Adjusting cropping seasons

- Integrated nutrient management

- Agro-forestry

- Irrigation schemes

E.1.2 Livestock

57. What are the top three priority technologies for Livestock?

- Livestock disease control

- Livestock health promotion

- Feeds and feeding improvement

- Selective breeding via controlled mating

- Early warning systems and insurance

- Biotechnology techniques (genetic improvement)

E.1.3 Fishery

58. What are the top three priority technologies for fishery production?

- Closed containment

- Aquaculture

- Smart fishing and weighing

- Advanced storage system

E.1.4 Forestry

59. What are the top three priority technologies for the forestry sub-sector?

i. Precision forestry (Unmanned Aerial Systems)

ii. Sustainable forestry management

iii. Flood and drought management

iv. Research tools

E.2. Water resources sector

60. What is the top priority sub-sector for climate change mitigation in Laos' water resources sector?

i. Water sources and supply management

ii. Water quality management

iii. Flood and drought management

- Water efficiency

61. What is the second priority sub-sector for climate change mitigation in Laos' water resources sector?

i. Water sources and supply management

ii. Water quality management

iii. Flood and drought management

iv. Water efficiency

62. What is the third priority sub-sector for climate change mitigation in Laos' water resources sector?

i. Water sources and supply management

ii. Water quality management

iii. Flood and drought management

iv. Water efficiency

E.2.1. Water sources and supply management

63. What are the top four priority technologies for water sources and supply management?

i. Watershed management (IWRM)

ii. Ground water pump

iii.Multi-purpose hydropower dam

iv.Irrigation

v.Borehole/Tube wells

vii.Rain water harvesting

- Water safety plan

E.2.2. Water quality management

64. What are the top four priority technologies for water quality management?

i. Water quality monitoring

ii. Effective law enforcement

iii. Water treatment plants

- Water recycles

- Water drainage system

- Household drinking water treatment and safe storage

- River bank protection

E.2.3. Flood and drought management

65. What are the top four priority technologies for flood and drought management?

i. Early warning system

ii. Flood and drought hazard mapping

iii. Flood and drought monitoring

iv.Improve weather forecast system

v.Regulation of water discharge (from dam)

vi. Preservation of wetland

E.2.4. Water efficiency

66. What is the top priority technology for water efficiency?

i. Water resources awareness and education

ii. Smart sensors for distribution

E.3. Transport and urban development sector

67. What is the top priority sub-sector for climate change mitigation in Laos' transport and urban development sector?

i. Airlines

ii. Marine

iii.Road

iv.Rail,

v.Transportation infrastructure

68. What is the second priority sub-sector for climate change mitigation in Laos' transport and urban development sector?

i. Airlines

ii. Marine

iii.Road

iv.Rail,

v.Transportation infrastructure

69. What is the third priority sub-sector for climate change mitigation in Laos' Transport and urban development sector?

i. Airlines

ii. Marine

iii.Road

iv.Rail

v.Transportation infrastructure

E.3.1. Airlines

70. What are the top three priority technologies for Airlines?

i. Energy management strategy

ii. Robotics

iii. Digital Twins

iv. AI & Machine Learning

E.3.2. Marine

71. What are the top three priority technologies for Marine sub-sector?

i. Energy management strategy

ii. Robotics

iii. Digital Twins

iv. AI & Machine Learning

E.3.3. Road

72. What are the top three priority technologies for Road sub-sector?

i. Energy management strategy

ii. Robotics

iii. Digital Twins

iv. AI & Machine Learning

E.3.4. Rail

73. What are the top three priority technologies for Rail sub-sector?

i. Energy management strategy

ii. Robotics

iii. Digital Twins

iv. AI & Machine Learning

E.3.5. Transport and infrastructure

74. What are the top three priority technologies for transport and infrastructure?

i. Energy management strategy

ii. Robotics

iii. Digital Twins

iv. AI & Machine Learning

E.4. Energy sector

75. What is the top priority sub-sector for climate change mitigation in Laos' energy sector?

- Solar energy generation

- Hydro energy generation

- Wind energy generation

- Gas-based generation

- Coal-based generation

- Nuclear power generation

76. What is the second priority sub-sector for climate change mitigation in Laos' energy sector?

- Solar energy generation

- Hydro energy generation

- Wind energy generation

- Gas-based generation

- Coal-based generation

- Nuclear power generation

77. What is the third priority sub-sector for climate change mitigation in Laos' energy sector?

- Solar energy generation

- Hydro energy generation

- Wind energy generation

- Gas-based generation

- Coal-based generation

- Nuclear power generation

E.4.1. Solar energy generation

78. What is the top priority technology for solar energy generation?

i. Solar thermal

ii. Concentrating solar power

iii. Small photovoltaic

iv. Large photovoltaic

E.4.2. Hydro energy generation

79. What is the top priority technology for hydro energy generation?

i. Hydro turbine

ii. Hydrokinetic turbines

E.4.3. Wind energy generation

80. What is the top priority technology for wind energy generation?

i. Onshore Wind

ii. Offshore Wind

E.4.4. Gas-based generation

81. What are the top two priority technologies for wind energy generation?

i. Conventional combustion turbine

ii. Advanced combustion turbine

iii.Natural gas combined cycle

iv.Advanced natural gas combined cycle

E.4.5. Gas-based generation

82. What are the top two priority technologies for wind energy generation?

i. Single Unit APC

ii. Double Unit APC

iii.Single Unit APC with CCS

iv.Double Unit APC with CCS

E.5. Industry sector

83. What is the top priority sub-sector for climate change mitigation in Laos' industry sector?

- Mineral industry

- Chemical industry

- Metal Production

- Food products

84. What is the second priority sub-sector for climate change mitigation in Laos' industry sector?

i.	Mineral industry

ii. Chemical industry

iii. Metal Production

iv. Food products

85. What is the third priority sub-sector for climate change adaptation in Laos' energy sector?

i. Mineral industry

ii. Chemical industry

iii. Metal Production

iv. Nuclear power generation

v. Food products

E.5.1. Mineral industry

86. What is the top priority technology for the mineral industry?

i. Cement production

ii. Glass production

iii. asphalt roofing production

E.5.2. Chemical industry

87. What is the top priority technology for the chemical industry?

i. Ammonia and urea fertilizer

ii. Nacl

C.5.3. Metal Production

89. What is the top priority technology for metal production?

i. Steel

ii. Ferroalloy production

C.5.4. Food products

90. What is the top priority technology for food production?

i. Soft drinks/beverages

ii. Alcoholic drinks

iii. Sugar

iv. Flour products (biscuits, pasta etc)