# Anne A I

# TERMS OF REFERENCE- 100005548

Project Title: 	Technology Needs Assessment for Climate Change Adaptation and Mitigation Technology in Lao PDR

Contents

Background	2

1)	GGGI’s Mission and Approach	2

2)	Background and Objectives	2

2.1. Background	2

2.2. Objective and Design	2

Proposed Activities and Scope of Work	2

1)	Scope of Work	2

2)	Deliverables	3

1. Deliverable 1 – Inception report (Week 2)	3

2. Deliverable 2 – Mid-term report (Months 1.5)	4

3. Deliverable 3 – Draft final report (Months 2.5)	4

4. Deliverable 4 – Final report and slide deck (Month 3)	4

Deliverables and Payment Schedule	4

Timetable and Reporting Arrangements	5

1)	Timetable	5

2)	Reporting Arrangements	5

Suggested Methodology	5

Competence Requirements and Allocation	6

Environmental and Social Considerations	6

Evaluation Criteria and Method	6

1)	Evaluation of Technical Component	7

2)	Evaluation of Financial Component	7

3)	Evaluation of Financial Soundness	8

4)	Evaluation of Technical and Financial components for total scoring	9

# Background

## GGGI’s Mission and Approach

Based in Seoul, The Global Green Growth Institute (GGGI) is an intergovernmental organization founded to support and promote a model of economic growth known as "green growth," which targets key aspects of economic performance such a poverty reduction, job creation, social inclusion, and environmental sustainability. GGGI works with countries around the world, building their capacity and working collaboratively on green growth policies that can impact the lives of millions. The organization partners with countries, multilateral institutions, government bodies, and private sectors to help build economies that grow strongly and are more efficient and sustainable in using natural resources, less carbon intensive, and more resilient to climate change.

## Background and Objectives

### 2.1. Background

GGGI, in collaboration with the Green Climate Fund (GCF), Korea Development Bank (KDB), and the governments of Cambodia, Indonesia, Laos and the Philippines, seeks to accelerate the deployment of climate technologies at scale through the Climate Technopreneurship Project (hereafter referred to as the “Project”). This will be achieved through, among others, (i) incubator/accelerator services for shortlisted start-ups, (ii) an investment fund, and (iii) other technical assistance tailored to the needs of each country. The ultimate goal of the Climate Technopreneurship Project is to match up selected local startups with global tech firms for technology transfer, and provide funding to newly established Joint Ventures or partnership entities for climate technology deployment. So, the purpose of this preparatory work by consultant would be to identify candidate technologies that are suitable for this project goal.

### 2.2. Objective and Design

The Consultant will support the preparatory phase of the Project by conducting a needs assessment for climate change adaptation and mitigation technologies in Laos (hereafter referred to as the “Report”). When drafting the Report, the Consultant should:

- Identify priority sectors for Laos to meet its adaptation and mitigation goals

- (For each sector) Identify priority technologies based on accepted process and criteria

- (For each sector and from the list of priority technologies) Recommend technologies for business incubation/acceleration or technology transfer/diffusion.

- Identify and map key stakeholders in Laos to be consulted with, including conduct consultations with key stakeholders and conduct stakeholders input analysis.

The duration of this assignment is 3 months.

# Proposed Activities and Scope of Work

- Scope of Work

Note. When identifying priority sectors and technologies, the Consultant should use the categorization scheme and terminology used by Climate Technology Centre & Network (CTCN) as a starting point.

- Identify priority sectors and subsectors (at least 5 sectors) for Lao PDR to meet its adaptation and mitigation goals, in consideration of:

- Relevant government plans and strategies including national socio-economic development plans, NDC, TNA, NGGS, NAMA, GCF country planning, SDGs, etc.

- Market assessment and stakeholder interviews/consultations.

- For priority sector and/or subsectors in Task 1, identify and evaluate priority technologies based on accepted key criteria (e.g. country needs, financial viability, technology feasibility, market/commercial availability, business potential, etc.) and their potential expected mitigation and /adaptation benefits impacts.

- The consultant will need to establish criteria for technology evaluation in coordination with GGGI, and agree in advance. The consultant can refer to the process and criteria developed by UNEP DTU when prioritizing technologies (see “TNA Step by Step: A Guidebook for Countries Conducting a Technology Needs Assessment and Action Plan”, pg. 21).

- The consultant should review the existing TNA of Laos, particularly priority sectors and technologies identified in such TNAs. Explore new technologies that are not included in those TNA, and update the technologies in the existing TNA.

- For the sectors not included in the previous TNA, identify priority technologies for both adaptation and mitigation using the agreed criteria. the Consultant must ensure that the Report is aligned with the contents of previous TNA.

- The Consultant may be requested to collect relevant data for the estimation of potential mitigation/adaptation impacts and co-benefits by GGGI.

- (For each sector and from the list of priority technologies), recommend technologies for business incubation/acceleration and/or technology transfer/diffusion (from global tech companies to local start-ups), highlighting current gaps and barriers as well as interventions to address them.

- The consultant will again need to establish criteria providing justification why the technologies are recommended. (e.g: technology feasibility, market/commercial availability, business potential, etc.); and based on the result of the Assessment of the Entrepreneurial Ecosystem for Climate Change Adaptation and Mitigation Technology in Lao PDR.

- The criteria will be developed in coordination with GGGI and agree in advance.

- Then, the Consultant may organize this section by starting with (i) the list of recommended technologies, followed by subsections that include (ii) barrier identification and analysis, (iii) interventions to address the barriers, and (iv) concrete action plans and ideas.

- Identify and map key stakeholders in Laos, obtain and analyze stakeholders’ inputs:

- Key stakeholders to be consulted should include, but not limited to: Relevant government and public entities; Local incubators and accelerators; Entrepreneurs; Venture capital (VC); Civil and Society Organisations (CSOs); and others such as development partners.

- Identify and map the key stakeholders involved in the climate change adaptation and mitigation technologies.

- Conduct interviews/consultations with key stakeholders to gather inputs and comments on the Point 1, 2 and 3 and analyse stakeholder’s inputs for the programme success.

NOTE: Gender should be considered and reflected throughout this assessment.

- Deliverables

### 1. Deliverable 1 – Inception report (Week 2)

- Identify sectors and relevant stakeholders to analyze. The Consultant should, within two weeks of contract signing, submit a tentative list of sectors to be analyzed. The Consultant should also provide a list of references and meeting minutes on which the list is based.

- Draft an annotated table of contents. The Consultant should submit an annotated table of contents with sections/sub-sections and 2-3 bullet points explaining the contents thereof.

- Prepare a workplan. The Consultant shall prepare a workplan with milestones. The workplan should include a list of persons/entities to be interviewed.

- Submit draft questionnaires to be used during interviews

### 2. Deliverable 2 – Mid-term report (Months 1.5)

- Conduct interviews. The Consultant should rely on interviews (in-person or remote) as his/her primary means of gathering information, starting with the stakeholder list in the latest TNA.

- Submit the mid-term report. The mid-term report should contain sections 1 – 4 (as described in “Scope of Work” above).

### 3. Deliverable 3 – Draft final report (Months 2.5)

- Submit the draft final report. The draft final report should contain sections 1 – 4 (as described in “Scope of Work” above). The draft final report should have addressed comments made by GGGI on the mid-term report.

### 4. Deliverable 4 – Final report and slide deck (Month 3)

- Revise and finalize the draft report and summary slide deck. The Consultant shall submit the revised and final Report and a summary slide deck by the end of Month 3.

# Deliverables and Payment Schedule

The expected outputs of the Consultant are as follows:

| Description of deliverables |  | Payment (% of total contract value) | KPI |
| --- | --- | --- | --- |
| Deliverable 1: Inception report |  | 20% |  |
| 1.1 | Annotated table of contents |  | Written approval by GGGI of submitted (i) documents and (ii) cover letter. |
| 1.2 | List of sectors and stakeholders to analyze |  |  |
| 1.3 | Workplan |  |  |
| 1.4 | List of questionnaires |  |  |
| Deliverable 2: Mid-term report |  |  |  |
| 2.1 | Meeting minutes of interviews |  | Written approval by GGGI of submitted (i) documents and (ii) cover letter. |
| 2.2 | Report with sections 1 – 4. |  |  |
| Deliverable 3: Draft final report |  | 50% |  |
| 3.1 | Report with sections 1 – 4 and GGGI’s comments on the mid-term report fully addressed. |  | Written approval by GGGI of submitted (i) documents and (ii) cover letter. |
| Deliverable 4: Final report |  | 30% |  |
| 4.1 | Final report |  | Written approval by GGGI of submitted (i) documents and (ii) cover letter. |
| 4.2 | Summary slide deck |  |  |
| Total |  | USD * |  |

* Note. VAT included.

- All reports must be both English (United States usage) prepared in accordance with GGGI’s formatting requirement, and submitted in electronic formats along with complete sets of raw data, research materials, and related information.

- Costs related to multi-stakeholder convenings will be covered by GGGI.

- The consultant is responsible for his/her own travel within Vientiane Capital and no transportation cost will be covered by GGGI.

- The Consulting firm shall consider the comments and necessary revisions proposed within 14 days from the receipt of the comments or modification proposal from the GGGI.

# Timetable and Reporting Arrangements

- Timetable

This project is expected to be completed within 3 months of start date (October 18, 2021, to January 18, 2022) with a tentative timetable as follows:

- Inception report – Within two weeks of contract signing

- Mid-term report – Within 1.5 months of contract signing

- Draft final report – Within 2.5 months of contract signing

- Final report – Within 3 months of contract signing

- Reporting Arrangements

The Consultant’s work progress will be monitored primarily through periodic review meetings, the precise schedule of which is to be determined based on consultation with the Consultant. The Consultant is also expected to periodically produce, upon GGGI’s request, a formal progress report that includes: an overview of the project, a narrative description of project activities, detailed information on project objectives and milestones, actual achievements made against the timeline set, etc. The progress report may be in Microsoft Word, PowerPoint, or Excel format.

# Suggested Methodology

Importance of consultations in prioritizing technologies. While desktop review can serve as a good starting point, we strongly advise the Consultant to organize sound workshops as inputs for the prioritization process. The Consultant should prepare the workshop agenda, background materials, and questionnaire (if applicable) in advance and share them with GGGI staff before organizing the workshops. The Consultant may have one-on-one meetings with key stakeholders before the workshop to ensure they are fully prepared and provide pertinent input on the day of.

If in-person workshops are not feasible due to COVID-19 related restrictions, the Consultant must prepare an alternative approach as soon as possible and no later than 3 weeks after contract signing.

# Competence Requirements and Allocation

Extensive experience in the preparation of NDCs, TNAs/TAPs, and national policies/strategies concerning climate change adaptation and mitigation technologies. We strongly prefer a team with at least one member who has at least 8 years extensive experience formulating national policies, roadmaps, or strategies concerning climate change adaptation and mitigation technologies. This individual would have an in-depth understanding of Laos’ climate technology needs in the short, medium, and long term (in light of the targets in its NDC and the feasibility of their adoption). He/she would also have a good relationship with stakeholders who should be part of the consultation process when prioritizing sectors and technologies.

Technical researcher/writer. This individual would have at least 8 years’ experience working as a technical researcher/writer. We would prefer someone who is fluent in both Lao and English.

Support staff. Given the breadth of this assignment, we would favor a team that provides adequate research and coordination support.

# Environmental and Social Considerations

N/A

# Evaluation Criteria and Method

From the last time and date of submission of the Quotations to the time the Contract is awarded, if any Tenderer wishes to contact the GGGI on any matter related to its Proposal, it should do so via the GGGI e-Green Procurement Portal (https://in-tendhost.co.uk/gggi).

Tenders will not be opened by GGGI until after the deadline for submission of Proposals. The Technical Component will be opened at one opening event, soon after the submission date, be listed in an opening protocol, submitted to, and thereafter be evaluated by the Procurement Committee, without unnecessary delay. The Procurement Committee, which has been appointed in according with GGGI’s Procurement Rules, will first perform a Technical Evaluation. The Tenders that have passed the Technical Evaluation will thereafter be subject to a Financial Evaluation, which includes a calculation of the total scoring for both the Technical and the Financial Evaluation, in accordance with the formula presented below. The Financial Component will not be opened until after the Technical Evaluation is finalized, and then by a corresponding procedure.

Selection will be based on the following process. The total possible score for the Technical component is maximum 100 points. 70% of the score received in the technical evaluation will be added to the obtained financial score, which is maximum 30 points, and calculated as described below.

The maximum budget available for this Contract is USD 24,000 , inclusive of any VAT or other taxes or costs.

Please, note that we do not recommend this maximum amount as a ‘target’ for your Quotation. The evaluation is a result of a combination of technical soundness and cost effectiveness of the Quotations, i.e. the evaluation of the financial component will be added to the evaluation result of the technical component, in accordance with the principles and weights set out in this document.

- Evaluation of Technical Component

A Proposal will be rejected at this stage if it fails to respond to important aspects of the Terms of Reference or to achieve a minimum technical score of 70.

The detailed technical evaluation criteria and possible scores for each are as follows:

| Major Criteria | Details & Sub-Criteria | Sub-score | Total maximum score |
| --- | --- | --- | --- |
| Firm/consultant’s experience (Subtotal: 30) | At least 8 years of experience in projects that involve a landscape analysis of climate change adaptation and/or mitigation technologies; experience preparing TNAs. | 15 | 30 |
|  | In-depth understanding of sectors and associated technologies that are relevant for climate change adaptation and/or mitigation, with at least 8 years of experience. | 15 |  |
| Methodology (Subtotal: 30) | Technical soundness of Deliverable 1 | 10 | 30 |
|  | Technical soundness of Deliverable 2 | 10 |  |
|  | Technical soundness of Deliverables 3 and 4 | 10 |  |
| Qualification of the team and task allocation (Subtotal: 40) | At least one team member with previous experience involving the formulation of NDCs, TNAs, GCF Country Programs, or comparable work on climate change adaptation/mitigation technologies. Minimum 8 years’ experience. | 30 | 40 |
|  | At least one team member with minimum 8 years’ experience as a technical researcher/writer related to technologies. | 5 |  |
|  | Team composition other than the two individuals mentioned above. Emphasis on whether there is sufficient manpower to provide (i) support to the technical writer on research/writing and (ii) support to the climate technology expert on the preparation of consultation materials, overall coordination, and follow-up activities. | 5 |  |
| Total Possible Technical Score |  |  | 100 |

- Evaluation of Financial Component

The maximum score for the financial component is 30 points. The maximum score shall be allocated to the lowest priced Proposal.  All other Proposals shall receive points in inverse proportion according to the following formula:

p = y * ( x / z )

where:

p  =  points for the financial Proposal being evaluated.

y  =  maximum number of points for the financial Proposal.

x  =  price of the lowest priced Proposal.

z  =  price of the Proposal being evaluated.

- Evaluation of Financial Soundness

The tenderer must demonstrate that its financial resources, less its financial obligations for its current contract commitments, meet or exceed the total requirement for the subject contract of USD24000. Information will be verified from Annual Financial Statements and any other documents that verifies the availability of financial resources submitted by the tenderer.

Special notes on financial proposal

Financial Proposal:

Following things will be checked:

1. The quantities and items are consistence with technical proposal

2. Prices offered are fair and in line with current market or industry trends

3. Reasonable to the GGGI

4. Rates are balanced

Compare technical and finance offers line by line and item by item before submission.

Financial Soundness:

Following will also be checked for financial soundness:

1. Current Ratio = (Current assets/Current liabilities)

The ideal current ratio is sometimes said to be 2 or minimum cash in hand as requested in TOR.

2. Quick Ratio also referred as acid test, the quick ratio tests an organizations true liquidity by assuming that stock is not immediately saleable.

Quick ratio = (Current assets) – (stock) /current liabilities

The ideal quick ratio is sometimes said to be 1

3. Check historical performance of the firm from financial statements to ensure that firm is not facing insolvency during contract duration

4. If financial statements are in local languages, please submit all documents in English translation

Direct and Indirect Tax:

Any liability of direct or indirect tax will remain with the consultant as per  local /national applicable laws, for example if tax (direct or indirect)  is applicable on payments from outside the country of the firm ( where firm is based) as per local laws , the consultant is liable to pay;   or in case tax law in countries of assignment  impose taxes on offshore services on foreign non-registered firms, the consultant is liable to pay their liabilities in accordance with national laws. It is a duty of the firm to conduct its own due diligence on tax liabilities before submission of proposals.

- Evaluation of Technical and Financial components for total scoring

The score for the technical component is added to the score for the financial component to arrive at the total score for a Proposal.  The Proposal with the overall highest score after this is the best Proposal.  The other Proposals will be ranked in descending numerical order based on the total score.